## Test Plan
Test Plan
mPower Social Enterprises Ltd.
Project |  | Prepared By |  | Date | Approved By
BDRIS Dashboard JIRA version 1.0.1 |  | Umme Maria |  | 2024-07-14 | Mojammel Hossain
Sl. No. | Name of Feature |  |  | Time Required (hrs) | No. of Resource Allocated
1 | SRS Review & Test Case Writing |  |  | 16 | 1
2 | Data preparation for database |  |  | 16 | 1
3 | Reports |  |  | 48 | 1
4 | System Administration |  |  | 8 | 1
5 | Notification |  |  | 8 | 1
|  |  |  | Hours for 1 tester | 96 | 12 | Days
|  |  |  | Hours for 2 tester | 0 |  | Days
|  |  |  | Test Plan for |  | 12 | Days
~ Test cycle will start date >>> 14/07/2024
~ This plan is only for the functional testing of the application. The time for regression cycle(s) will depend on the number of bugs and change requests yet to come. [Generally the time for regression testing = ½ the time for functional testing.]